## project_plan_sample
SNo | WBSCode | TaskName | StartDate | FinishDate | DurationDays | Predecessors | Responsibility
1 | 1 | Mobilisation & Site Setup | 2026-06-01 | 2026-06-07 | 7 |  | PM
2 | 1.1 | Site clearance & fencing | 2026-06-04 | 2026-06-13 | 10 | 1 | Site Engineer
3 | 1.2 | Setting out & benchmarks | 2026-06-06 | 2026-06-11 | 6 | 1 | Surveyor
4 | 2.1 | Excavation for foundations | 2026-06-12 | 2026-07-01 | 20 | 1.1;1.2 | Site Engineer
5 | 2.2 | PCC for foundations | 2026-06-19 | 2026-07-03 | 15 | 2.1 | Site Engineer
6 | 2.3 | RCC footing casting | 2026-06-23 | 2026-07-11 | 19 | 2.2 | Structure Engineer
7 | 2.4 | Plinth beam & backfilling | 2026-07-06 | 2026-07-26 | 21 | 2.3 | Structure Engineer
8 | 3.1 | Ground floor columns & slab | 2026-07-21 | 2026-08-25 | 36 | 2.4 | Structure Engineer
9 | 3.2 | Typical floor 1 columns & slab | 2026-08-20 | 2026-09-24 | 36 | 3.1 | Structure Engineer
10 | 3.3 | Typical floor 2 columns & slab | 2026-09-19 | 2026-10-24 | 36 | 3.2 | Structure Engineer
11 | 3.4 | Typical floor 3 columns & slab | 2026-10-19 | 2026-11-23 | 36 | 3.3 | Structure Engineer
12 | 3.5 | Typical floor 4 columns & slab | 2026-11-18 | 2026-12-23 | 36 | 3.4 | Structure Engineer
13 | 4.1 | Brickwork & blockwork all floors | 2026-08-30 | 2027-01-12 | 136 | 3.2 | Masonry Contractor
14 | 4.2 | Internal plastering | 2026-10-19 | 2027-02-06 | 111 | 4.1 | Masonry Contractor
15 | 4.3 | External plastering | 2026-11-28 | 2027-02-16 | 81 | 4.1 | Masonry Contractor
16 | 5.1 | Waterproofing terraces & toilets | 2026-12-08 | 2027-02-01 | 56 | 3.5 | Specialist Vendor
17 | 5.2 | Flooring & dado | 2026-12-28 | 2027-03-08 | 71 | 4.2;5.1 | Finishing Contractor
18 | 5.3 | Doors, windows & hardware | 2027-01-07 | 2027-03-13 | 66 | 4.2 | Joinery Vendor
19 | 6.1 | Electrical & plumbing fixtures | 2027-01-17 | 2027-03-18 | 61 | 5.2;5.3 | MEP Contractor
20 | 6.2 | Final painting & touchup | 2027-02-16 | 2027-03-28 | 41 | 5.2;6.1 | Finishing Contractor
21 | 7.1 | Testing, commissioning & snagging | 2027-03-18 | 2027-04-17 | 31 | 6.2 | PM
22 | 7.2 | Handover & demobilisation | 2027-04-17 | 2027-04-27 | 11 | 7.1 | PM